## Executive Dashboard
TRAKSLIP CONSTRUCTION T&M EXECUTIVE DASHBOARD
⚡ 100% FORMULA WORKBOOK: Click any cell below to see dynamic =SUMIF(), =COUNTIF(), and cross-sheet formulas.
TOTAL T&M TRACKED | APPROVED & BILLED | PENDING GC SIGN-OFF | UNDER REVIEW / DISPUTED | % PORTFOLIO BILLED
41425.5 | 28588.5 | 7832 | 5005 | 69%
1. Subcontractor Trade Specialty Breakdown (Formulas)
Trade Specialty | Ticket Count | Approved Billed ($) | Pending / Review ($) | % Billed Ratio
Electrical Contractor | 4 | 9731.5 | 5005 | 66.04%
Mechanical / HVAC | 3 | 3602 | 6259 | 36.53%
Plumbing Subcontractor | 3 | 3542 | 2727 | 56.5%
Drywall & Framing | 3 | 4715 | 0 | 100%
Structural Steel | 2 | 6998 | 0 | 100%
Total Portfolio Summary | 15 | 28588.5 | 13991 | 67.1%
2. Portfolio Cost Breakdown by Category (Formulas)
Cost Category | Formulas Reference | Total Amount ($) | % of Total Value
Labor Costs | SUM('Master T&M Ticket Log'!F4:F30) | 17318.5 | 41.81%
Equipment Rentals | SUM('Master T&M Ticket Log'!G4:G30) | 5680 | 13.71%
Material Purchases | SUM('Master T&M Ticket Log'!H4:H30) | 14710 | 35.51%
Contract Markups | SUM('Master T&M Ticket Log'!I4:I30) | 3717 | 8.973%
Total Verified Costs | SUM(D22:D25) | 41425.5 | 100%

## Master T&M Ticket Log
MASTER TIME AND MATERIAL (T&M) FIELD TICKET LOG
Ticket ID | Date | Subcontractor / Trade | Location / Grid | Scope Description | Labor ($) | Equipment ($) | Material ($) | Markup ($) | Total Value ($) | GC Approval Status | Signed By / Verification
TM-2026-001 | 2026-08-01 | ABC Electrical | Floor 3 - Area B | Relocate conduit interfering with HVAC ductwork | 928.5 | 275 | 1240 | 246 | 2689.5 | APPROVED | J. Smith (GC Super)
TM-2026-002 | 2026-08-02 | Apex Plumbing | Basement Core | Emergency pump out of standing groundwater | 640 | 450 | 310 | 140 | 1540 | APPROVED | J. Smith (GC Super)
TM-2026-003 | 2026-08-03 | Vanguard HVAC | Roof Deck West | Additional crane rigging for revised chiller location | 1450 | 1200 | 480 | 313 | 3443 | PENDING SIGNATURE | Pending Field Sign
TM-2026-004 | 2026-08-04 | Precision Drywall | Floor 2 - Room 204 | Demo and rebuild shaft wall per ASI-014 | 1120 | 150 | 890 | 216 | 2376 | APPROVED | M. Davis (PM)
TM-2026-005 | 2026-08-05 | ABC Electrical | Exterior South | Temp power feed install for tower crane | 1850 | 600 | 2100 | 455 | 5005 | UNDER REVIEW | Disputed Rates
TM-2026-006 | 2026-08-06 | Titan Steel | Grid A-4 Column | Weld reinforcement plates due to RFI-088 shift | 1350 | 400 | 650 | 240 | 2640 | APPROVED | J. Smith (GC Super)
TM-2026-007 | 2026-08-07 | Apex Plumbing | Floor 4 Restrooms | Reroute waste line for structural beam clash | 880 | 200 | 740 | 182 | 2002 | APPROVED | J. Smith (GC Super)
TM-2026-008 | 2026-08-08 | Vanguard HVAC | Mechanical Room | Install extra fire dampers required by inspector | 960 | 180 | 1420 | 256 | 2816 | PENDING SIGNATURE | Sent via Email
TM-2026-009 | 2026-08-09 | Precision Drywall | Lobby Ceiling | Soffit framing detail change per Architect memo | 1240 | 220 | 560 | 202 | 2222 | APPROVED | M. Davis (PM)
TM-2026-010 | 2026-08-10 | ABC Electrical | Floor 5 Data Room | Pull dedicated feed for UPS backup rack | 1050 | 300 | 1850 | 320 | 3520 | APPROVED | J. Smith (GC Super)
TM-2026-011 | 2026-08-11 | Titan Steel | Mezzanine South | Modify stair stringer attachment for structural clearance | 1600 | 550 | 920 | 307 | 3377 | APPROVED | J. Smith (GC Super)
TM-2026-012 | 2026-08-12 | Apex Plumbing | Penthouse Mech | Install high-pressure relief valve system | 1150 | 320 | 1100 | 257 | 2827 | PENDING SIGNATURE | Pending Field Sign
TM-2026-013 | 2026-08-13 | Vanguard HVAC | Floor 1 West | Extend ductwork for revised conference room layout | 1380 | 250 | 1450 | 308 | 3388 | APPROVED | M. Davis (PM)
TM-2026-014 | 2026-08-14 | ABC Electrical | Garage Level 1 | Repair lighting conduit damaged by excavation crew | 820 | 190 | 640 | 165 | 1815 | APPROVED | J. Smith (GC Super)
TM-2026-015 | 2026-08-15 | Precision Drywall | Floor 6 Hallway | Patch dry wall after plumber pipe relocation | 750 | 100 | 320 | 117 | 1287 | APPROVED | M. Davis (PM)
TOTALS |  |  |  |  | 17318.5 | 5680 | 14710 | 3717 | 41425.5

## Labor Rates & Calculator
CONTRACTOR APPROVED LABOR RATE MATRIX & AUTOMATED FORMULAS
Trade Classification | Base Rate ($/hr) | Burden Rate ($/hr) | Total Cost ($/hr) | Markup % | Std Billing ($/hr) | OT Factor | OT Billing ($/hr) | DT Factor | DT Billing ($/hr)
Master Electrician | 55 | 22 | 77 | 15% | 88.55 | 1.5 | 132.825 | 2 | 177.1
Journeyman Electrician | 45 | 18 | 63 | 15% | 72.45 | 1.5 | 108.675 | 2 | 144.9
Electrician Apprentice | 28 | 11.2 | 39.2 | 15% | 45.08 | 1.5 | 67.62 | 2 | 90.16
HVAC Senior Technician | 52 | 20.8 | 72.8 | 15% | 83.72 | 1.5 | 125.58 | 2 | 167.44
Plumber Foreman | 56 | 22.4 | 78.4 | 15% | 90.16 | 1.5 | 135.24 | 2 | 180.32
Drywall Journeyman | 38 | 15.2 | 53.2 | 15% | 61.18 | 1.5 | 91.77 | 2 | 122.36
Structural Steel Welder | 58 | 23.2 | 81.2 | 15% | 93.38 | 1.5 | 140.07 | 2 | 186.76

## Equipment Rates
EQUIPMENT RENTAL & OPERATING RATE FORMULA MATRIX
Equipment Category / Type | Daily Rate ($) | Weekly Rate (3.5x) | Monthly Rate (3x Wk) | Hourly Operating ($/hr) | Fuel Surcharge (12%) | Total Billed ($/hr)
19ft Electric Scissor Lift | 150 | 525 | 1575 | 18.75 | 2.25 | 21
40ft Articulating Boom Lift | 350 | 1225 | 3675 | 43.75 | 5.25 | 49
Mini Excavator (Kubota KX040) | 400 | 1400 | 4200 | 50 | 6 | 56
Towable Diesel Generator 45kVA | 220 | 770 | 2310 | 27.5 | 3.3 | 30.8
Commercial Air Compressor | 120 | 420 | 1260 | 15 | 1.8 | 16.8
Concrete Core Drill Rig | 180 | 630 | 1890 | 22.5 | 2.7 | 25.2

## Materials & Markups
MATERIAL PURCHASES, TAX, FREIGHT & MARKUP FORMULA LOG
Ticket ID | Supplier / Vendor | Item Description | Invoice Subtotal | Freight (5%) | Sales Tax % | Tax Amount ($) | Material Cost | Markup % | Billed Total ($)
TM-2026-001 | Graybar Electric | Conduit, junction boxes, wire nuts | 1000 | 50 | 8.875% | 93.1875 | 1143.1875 | 15% | 1314.6656
TM-2026-002 | Ferguson Plumbing | Submersible pump & discharge hose | 250 | 12.5 | 8.875% | 23.2969 | 285.7969 | 15% | 328.6664
TM-2026-003 | United Rentals | Rigging straps and spreader bar | 390 | 19.5 | 8.875% | 36.3431 | 445.8431 | 15% | 512.7196
TM-2026-004 | US LBM Building | Metal studs, track & drywall sheets | 720 | 36 | 8.875% | 67.095 | 823.095 | 15% | 946.5592
TM-2026-005 | Anixter Supply | 4/0 Heavy copper feeder cable | 1700 | 85 | 8.875% | 158.4187 | 1943.4188 | 15% | 2234.9316
TOTALS |  |  | 4060 | 203 |  | 378.34 | 4641.34 |  | 5337.54

## Pay App Attachment
MONTHLY T&M CHANGE ORDER SUMMARY (AIA G702 / G703 ATTACHMENT)
Item # | Ticket ID | Description of Extra Work | Subcontractor Trade | Gross Billed ($) | Retainage (5%) | Net Payment Due ($) | GC Status
1
2
3
4
5
6
7
8
9
10
TOTALS